## Workbook
Project budget
Original editable starter. Fictional example data. Replace blue inputs; keep black formulas.
Work package | Owner | Budget USD | Actual USD | Variance USD | Note | Summary | Value
Research | Avery | 2500 | 2300 | -200 | Explain material change | Budget total | 16700
Design | Morgan | 3200 | 3300 | 100 | Explain material change | Actual total | 15600
Development | Jordan | 6000 | 5800 | -200 | Explain material change | Variance | -1100
Testing | Casey | 1800 | 1900 | 100 | Explain material change
Content | Riley | 1200 | 1100 | -100 | Explain material change
Training | Taylor | 800 | 750 | -50 | Explain material change
Handover | Sam | 500 | 450 | -50 | Explain material change
Contingency | Alex | 700 | 0 | -700 | Explain material change
How to use
1. Define the budget scope. Choose work packages, currency and reporting period.
2. Enter planned and actual costs. Use consistent categories and source records.
3. Review the differences. Explain material changes before revising the plan.
Budget variance is not a measure of project value or completion.
Source: original fictional examples prepared for WPS Explore. No customer data is included.