## Workbook
Project charter
Original editable starter. Fictional example data. Replace blue inputs; keep black formulas.
Charter section | Draft content | Owner | Review status
Purpose | Reduce manual order entry | Project lead | For review
Objective | Create a consistent order intake workflow | Sponsor | For review
Scope | Order form, validation and handover guide | Project lead | Draft
Out of scope | Payment processing and warehouse integration | Sponsor | Draft
Deliverables | Approved form and operating guide | Project lead | Draft
Success criteria | Pilot orders can be reviewed without missing required fields | Operations | Draft
Assumptions | Operations team available for weekly review | Project lead | Draft
Constraints | Four-week pilot with existing tools | Sponsor | Draft
Risks | Delayed feedback may affect the pilot date | Project lead | Draft
Approval | Pending sponsor review | Sponsor | Not approved
How to use
1. Describe the need. Write the business problem and intended result.
2. Set the boundaries. List deliverables, exclusions, assumptions and constraints.
3. Review the agreement. Confirm owners and acceptance criteria with the sponsor.
The example is a planning aid. Approval is entered manually and is not an electronic signature.
Source: original fictional examples prepared for WPS Explore. No customer data is included.