## Workbook
Project plan
Original editable starter. Fictional example data. Replace blue inputs; keep black formulas.
Task ID | Deliverable | Owner | Start date | Due date | Predecessor | Status
P-01 | Approved brief | Avery | 2026-11-02T00:00:00.000Z | 2026-11-04T00:00:00.000Z | None | Open
P-02 | Research findings | Morgan | 2026-11-04T00:00:00.000Z | 2026-11-06T00:00:00.000Z | P-01 | In progress
P-03 | Design draft | Jordan | 2026-11-06T00:00:00.000Z | 2026-11-08T00:00:00.000Z | P-02 | Done
P-04 | Prototype | Casey | 2026-11-08T00:00:00.000Z | 2026-11-10T00:00:00.000Z | P-03 | Open
P-05 | Test report | Riley | 2026-11-10T00:00:00.000Z | 2026-11-12T00:00:00.000Z | P-04 | In progress
P-06 | Final copy | Taylor | 2026-11-12T00:00:00.000Z | 2026-11-14T00:00:00.000Z | P-05 | Done
P-07 | Release checklist | Sam | 2026-11-14T00:00:00.000Z | 2026-11-16T00:00:00.000Z | P-06 | Open
P-08 | Launch review | Alex | 2026-11-16T00:00:00.000Z | 2026-11-18T00:00:00.000Z | P-07 | Open
How to use
1. Define the deliverables. List the outputs required to finish the project.
2. Break down the work. Add tasks, owners, dates and predecessor references.
3. Review the sequence. Resolve conflicting dates and update status during delivery.
Dates and dependencies are manually maintained; this is not an automatic critical-path scheduler.
Source: original fictional examples prepared for WPS Explore. No customer data is included.