## Workbook
Project schedule
Original editable starter. Fictional example data. Replace blue inputs; keep black formulas.
Task ID | Task | Owner | Start date | Finish date | Predecessor | Status | Calendar days
P-01 | Approved brief | Avery | 2026-11-02T00:00:00.000Z | 2026-11-04T00:00:00.000Z | None | Open | 3
P-02 | Research findings | Morgan | 2026-11-04T00:00:00.000Z | 2026-11-06T00:00:00.000Z | P-01 | In progress | 3
P-03 | Design draft | Jordan | 2026-11-06T00:00:00.000Z | 2026-11-08T00:00:00.000Z | P-02 | Done | 3
P-04 | Prototype | Casey | 2026-11-08T00:00:00.000Z | 2026-11-10T00:00:00.000Z | P-03 | Open | 3
P-05 | Test report | Riley | 2026-11-10T00:00:00.000Z | 2026-11-12T00:00:00.000Z | P-04 | In progress | 3
P-06 | Final copy | Taylor | 2026-11-12T00:00:00.000Z | 2026-11-14T00:00:00.000Z | P-05 | Done | 3
P-07 | Release checklist | Sam | 2026-11-14T00:00:00.000Z | 2026-11-16T00:00:00.000Z | P-06 | Open | 3
P-08 | Launch review | Alex | 2026-11-16T00:00:00.000Z | 2026-11-18T00:00:00.000Z | P-07 | Open | 3
How to use
1. Define the task sequence. Use stable IDs and meaningful outputs.
2. Set start and finish dates. Check dependencies and owner availability.
3. Review changes. Update downstream dates when assumptions change.
The starter does not calculate an automatic critical path or working-day calendar.
Source: original fictional examples prepared for WPS Explore. No customer data is included.