## Workbook
Project timeline
Original editable starter. Fictional example data. Replace blue inputs; keep black formulas.
Phase | Start date | Finish date | Calendar days | Milestone | Dependency
Discovery | 2026-11-02T00:00:00.000Z | 2026-11-04T00:00:00.000Z | 3 | Brief approved | None
Requirements | 2026-11-05T00:00:00.000Z | 2026-11-07T00:00:00.000Z | 3 | Scope agreed | 1. Discovery
Design | 2026-11-08T00:00:00.000Z | 2026-11-10T00:00:00.000Z | 3 | Design accepted | 2. Requirements
Prototype | 2026-11-11T00:00:00.000Z | 2026-11-13T00:00:00.000Z | 3 | Prototype ready | 3. Design
Review | 2026-11-14T00:00:00.000Z | 2026-11-16T00:00:00.000Z | 3 | Feedback resolved | 4. Prototype
Build | 2026-11-17T00:00:00.000Z | 2026-11-19T00:00:00.000Z | 3 | Build complete | 5. Review
Validation | 2026-11-20T00:00:00.000Z | 2026-11-22T00:00:00.000Z | 3 | Checks passed | 6. Build
Handover | 2026-11-23T00:00:00.000Z | 2026-11-25T00:00:00.000Z | 3 | Owner accepts | 7. Validation
How to use
1. List the project phases. Use meaningful outputs to define the stages.
2. Set dates and milestones. Check the start and finish dates for each phase.
3. Review the sequence. Resolve impossible overlaps and update the timeline as plans change.
Durations count calendar days inclusively. Working-day calendars and automatic dependency scheduling are not
included.
Source: original fictional examples prepared for WPS Explore. No customer data is included.